## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Alec | Nate | Jordan | Tanvi | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 4 |  | 0
|  | Design architecture | Project Manager | Tanvi | 4 | [7 empty] | 0
| Requirements |  |  |  |  | 9 |  | 5 |  |  |  |  | 0
|  | Gather | Requirements Engineer | Nate | 3 |  | 2 |  |  | 2 |  |  | 2
|  | Analyze | Requirements Engineer | Nate | 3 |  | 1 |  |  | 1 |  |  | 1
|  | Specify | Requirements Engineer | Nate | 3 |  | 2 |  |  | 2 |  |  | 2
| Documentation |  |  |  |  | 32 |  | 12 |  |  |  |  | 5
|  | Project Charter | Project Manager | Tanvi, Nate, Alec, Jordan | 2 |  | 2 | [5 empty] | 0
|  | Release Plan | Project Manager | Tanvi | 4 | [7 empty] | 0
|  | Requirements Document | Requirements Engineer | Nate | 4 |  | 4 |  |  | 4 |  |  | 4
|  | Project Plan | Project Manager, Developers | Tanvi, Nate, Alec, Jordan | 6 |  | 6 |  |  | 3 | 3 |  | 6
|  | Architecture Document | Architect | Tanvi | 6 | [7 empty] | 0
|  | Test Report | Tester | Nate | 8 | [7 empty] | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Tanvi, Nate, Alec, Jordan | 2 | [7 empty] | 0
Coding | [12 empty] | 0
Iteration 1: | Development |  |  |  |  | 18.5 |  | 18.5 |  |  |  |  | 18.5
|  | Determine technology needs | Developer | Tanvi, Nate, Alec, Jordan | 1 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
|  | Learn the ASP.NET and C# Fundamentals | Developer | Tanvi, Nate, Alec, Jordan | 4 |  | 8 |  | 2 | 2 | 2 | 2 | 8
|  | Set up development environment and IDE | Developer | Tanvi, Nate, Alec, Jordan | 1 |  | 1 |  | 0.25 | 0.25 | 0.25 | 0.25 | 1
|  | Set up local servers | Developer | Tanvi, Nate, Alec, Jordan | 1 |  | 1 |  | 0.25 | 0.25 | 0.25 | 0.25 | 1
|  | Set up database table format | Developer | Alec, Nate | 1.5 |  | 1.5 |  | 1.5 | 0 |  |  | 1.5
|  | Generate test datasets | Developer | Jordan | 1 |  | 1 |  |  |  | 1 |  | 1
|  | Create sample title page with login | Developer | Tanvi | 4 |  | 2.5 |  |  |  |  | 2.5 | 2.5
|  | Add styling to title page | Developer | Tanvi | 2 |  | 0.5 |  |  |  |  | 0.5 | 0.5
|  | Create Standard Notification Rules | Developer | Nate | 1 |  | 1 |  |  | 1 |  |  | 1
|  | Unit testing | Tester | Nate | 2 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 4.5 |  | 4 |  |  |  |  | 4
|  | System Testing | Tester | Jordan | 0.5 |  | 0 |  |  |  | 0 |  | 0
|  | Fix any bugs | Developer | Jordan | 2 |  | 0 |  |  |  | 0 |  | 0
|  | Evaluate needs for next iteration | Project Manager | Tanvi, Nate, Alec, Jordan | 2 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Iteration 2: | Design |  |  |  |  | 6 |  | 5 |  |  |  |  | 0
|  | Design basic CSS styles for project | Developer | Tanvi, Nate, Alec, Jordan | 1 |  | 0.5 |  |  |  |  | 0.5 | 0.5
|  | Integrate hex codes for designing backgorund | Developer | Tanvi, Nate, Alec, Jordan | 1 |  | 0.5 |  |  |  |  | 0.5 | 0.5
|  | Set up database for username and password | Developer | Alec | 2 |  | 2 | [5 empty] | 0
|  | Set up database for transactions | Developer | Alec | 2 |  | 2 | [5 empty] | 0
| Development |  |  |  |  | 18 |  | 11 |  |  |  |  | 0
|  | Create a dashboard on the user homepage | Developer | Tanvi, Nate, Alec | 4 |  | 0 |  | 0 |  |  |  | 0
|  | Create a log-in screen,home page | Developer | Tanvi | 4 |  | 3 |  |  |  |  | 3 | 3
|  | Create a transaction flags page | Developer | Jordan | 4 |  | 3 |  |  |  | 3 |  | 3
|  | Create a transaction history page | Developer | Nate | 3 |  | 3 |  |  | 3 |  |  | 3
|  | Add registration form page for new user | Developer | Tanvi | 3 |  | 2 |  |  |  |  | 2 | 2
|  | Set up basic database integration | Developer | Alec, Nate, Tanvi, Jordan | 8 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 10 |  | 4 |  |  |  |  | 0
|  | System Testing | Tester | Tanvi, Nate, Alec, Jordan | 2 |  | 0 | [5 empty] | 0
|  | Fix found bugs | Developer | Tanvi, Nate, Alec, Jordan | 4 |  | 0 | [5 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Tanvi, Nate, Alec, Jordan | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Iteration 3: | Design |  |  |  |  | 3 |  | 1 |  |  |  |  | 0
|  | Maintain CSS Styling | Developer | Tanvi, Nate, Alec, Jordan | 1 |  | 1 |  |  |  |  | 1 | 1
|  | Use hex code for the dashboard | Developer | Tanvi | 2 |  | 0 | [5 empty] | 0
| Development |  |  |  |  | 25 |  | 13 |  |  |  |  | 0
|  | Create logic to add transactions | Developer | Alec | 2 |  | 0 |  | 0 |  |  |  | 0
|  | Create logic to add users | Developer | Jordan | 2 |  | 3 |  |  |  | 3 |  | 3
|  | Create a page for the user after logging in | Developer | Tanvi | 4 |  | 2.5 | [5 empty] | 0
|  | Create a dashboard with basic functionalities | Developer | Tanvi | 3 |  | 1 |  |  |  |  | 1 | 1
|  | Link the login page to the dashboard for user | Developer | Tanvi | 2 |  | 0.5 | [5 empty] | 0
|  | Create logic for transaction triggers | Developer | Alec | 5 |  | 0 |  | 0 |  |  |  | 0
|  | Continue development for transactions page | Developer | Nate | 3 |  | 1 |  |  | 1 |  |  | 1
|  | Continue development for flags page | Developer | Jordan | 4 |  | 5 |  |  |  | 5 |  | 5
|  | Develop the database tables for the app | Developer | Alec | 3 |  | 3 |  | 3 |  |  |  | 3
| Analysis |  |  |  |  | 10 |  | 4 |  |  |  |  | 0
|  | System Testing | Tester | Tanvi, Nate, Alec, Jordan | 2 |  | 0 | [5 empty] | 0
|  | Fix any bugs | Developer | Tanvi, Nate, Alec, Jordan | 4 |  | 0 | [5 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Tanvi, Nate, Alec, Jordan | 4 |  | 4 |  | 1 | 1 | 1 | 1
Total |  |  |  |  | 151 | 140 | 75.5 | 77.5 | 10.5 | 23 | 21 | 17 | 71.5